## Read Me
Hair Solutions Co - 90-Day Launch Content Calendar (FINAL v1.0)
Window | Aug 3 - Oct 31, 2026 (Day 1 = Mon Aug 3)
Cadence | Week 1: 3 feed posts/day (hero + 2 fillers). Days 8-90: 1 feed post/day. Stories daily.
Editable cells | Only the STATUS column (yellow) - values: Planned / Shot / Designed / Scheduled / Posted.
Example | Day 1 hero row shows STATUS = Planned as the expected format.
Flags column | Red text = blocker or verification needed before posting (consent, price check, claims).
Guardrails | No emoji or exclamation marks in copy. No medical claims. No fabricated testimonials - quote slots ship only with a real, consented source. Verify prices against live Shopify catalog.
Sale ceiling | Two promos only: Day 56 FIRST10 (Sep 27) and Day 82 FALL15 (Oct 23).
Source | Merged from: 90-Day Rebrand Strategy + Week 1 Launch Batch + Punch-List + Social Design Analysis. This file replaces all of them. 2026-07-19.

## Calendar 90 Days
Day | Date | Weekday | Phase | Slot | Format | Archetype | Hook / Headline | Pillar | Stories (concept - frames - stickers) | Flags | Status
1 | Mon Aug 03, 2026 | Mon | 1 - Opening Week | Hero | Static | wordmark (ink) | A new chapter starts today. | Brand | Launch day (Founder) - 4 frames: ink wordmark / Something's changed / lineage line (QUOTE-SHARE) / biggest question (Q-BOX) |  | Planned
1 | Mon Aug 03, 2026 | Mon | 1 - Opening Week | Filler | Static | quote | Same company. New standard. | Brand
1 | Mon Aug 03, 2026 | Mon | 1 - Opening Week | Filler | Static | typo | Not louder. Not different. Just clearer. | Brand
2 | Tue Aug 04, 2026 | Tue | 1 - Opening Week | Hero | Carousel x5 | manifesto carousel | For the man who wants to look like himself again. | Brand | Education - 4 frames: manifesto intro / mirror line (QUOTE-SHARE) / quiz (QUIZ) / save the guide (LINK)
2 | Tue Aug 04, 2026 | Tue | 1 - Opening Week | Filler | Static | typo | Confidence is not loud. | Brand
2 | Tue Aug 04, 2026 | Tue | 1 - Opening Week | Filler | Static | quote | We build for quiet confidence, not attention. | Brand
3 | Wed Aug 05, 2026 | Wed | 1 - Opening Week | Hero | Reel ~25s | founder reel | I wear what I sell. | Founder | Product/About - 3 frames: portrait BTS / one take natural light / daily-wear questions (LINK)
3 | Wed Aug 05, 2026 | Wed | 1 - Opening Week | Filler | Static | typo (ink) | Made for grown men. | Brand
3 | Wed Aug 05, 2026 | Wed | 1 - Opening Week | Filler | Static | photo | The desk where every system gets checked before it ships. | Founder
4 | Thu Aug 06, 2026 | Thu | 1 - Opening Week | Hero | Reel ~20s | explainer reel | This is not a wig. | Education | Q&A - 5 frames: intro / is it a wig / will people notice / how long it lasts / question box (Q-BOX)
4 | Thu Aug 06, 2026 | Thu | 1 - Opening Week | Filler | Static | product | Thin Skin Pro - $279 - 0.08mm poly base | Product |  | Verify price
4 | Thu Aug 06, 2026 | Thu | 1 - Opening Week | Filler | Static | product | Mono Pro - $299 - fine welded monofilament | Product |  | Verify price
5 | Fri Aug 07, 2026 | Fri | 1 - Opening Week | Hero | Static | product hero | Lace Elite, photographed honestly. (Swiss lace) | Product | BTS/QC - 4 frames: shooting Lace Elite / daylight hairline macro / base poll (POLL) / ask anything (LINK) | Verify price
5 | Fri Aug 07, 2026 | Fri | 1 - Opening Week | Filler | Static | product | Lace Fusion VF - $289 - lace front, clear PU perimeter | Product |  | Verify price
5 | Fri Aug 07, 2026 | Fri | 1 - Opening Week | Filler | Static | product | Micro Skin - $219 - 0.06mm V-loop | Product |  | Verify price
6 | Sat Aug 08, 2026 | Sat | 1 - Opening Week | Hero | Carousel x6 | how-it-works | Will the hairline look real? | Education | Founder - 3 frames: most-asked question / spotting-a-system slider (SLIDER) / carousel pointer (LINK)
6 | Sat Aug 08, 2026 | Sat | 1 - Opening Week | Filler | Static | quote over macro | A hairline should survive daylight. | Education
6 | Sat Aug 08, 2026 | Sat | 1 - Opening Week | Filler | Static | product | Skin Frontal - $169 - partial front piece | Product |  | Verify price
7 | Sun Aug 09, 2026 | Sun | 1 - Opening Week | Hero | Reel ~10s | testimonial reel | I forgot I was wearing it. | Social Proof | Week preview - 4 frames: week one done / deeper-topic poll (POLL) / next week tease / Monday countdown (COUNTDOWN) | BLOCKED: real consented quote required; swap with Day 8 QC reel if not ready
7 | Sun Aug 09, 2026 | Sun | 1 - Opening Week | Filler | Static | typo | Ordering online should not feel like gambling. | Brand |  | No refund/shipping claims
7 | Sun Aug 09, 2026 | Sun | 1 - Opening Week | Filler | Static | product | Nano Skin - $269 - 0.03mm ultra-thin poly | Product |  | Verify price
8 | Mon Aug 10, 2026 | Mon | 2 - Foundation | Hero | Reel ~30s | founder QC reel | Before it ships, I check this. (3 things I check) | Founder | Motivation - 3 frames: standard is personal (QUOTE-SHARE) / QC desk / reel pointer (LINK)
9 | Tue Aug 11, 2026 | Tue | 2 - Foundation | Hero | Carousel x7 | decision carousel | New here? Start with these 5 decisions. | Education | Tips - 3 frames: base first / blocking decision (Q-BOX) / save guide (LINK)
10 | Wed Aug 12, 2026 | Wed | 2 - Foundation | Hero | Static | product | Mono Pro - Silent, breathable, structured. | Product | Product - 3 frames: benefits / macro weave / specs (LINK) | Verify price
11 | Thu Aug 13, 2026 | Thu | 2 - Foundation | Hero | Static | quote | Three months in. My wife noticed first. | Social Proof | Q&A - 4 frames: intro / gym question / first-time cost / question box (Q-BOX) | REQUIRES REAL QUOTE + consent
12 | Fri Aug 14, 2026 | Fri | 2 - Foundation | Hero | Static | typo editorial | Why hair systems aren't toupees. | Education | BTS - 4 frames: studio Friday / writing education / myth poll (POLL) / weekend tease
13 | Sat Aug 15, 2026 | Sat | 2 - Foundation | Hero | Reel ~10s | product macro reel | Lace Elite. Knot to tip. | Product | Lifestyle - 2 frames: Rio Saturday (SLIDER) / reel live (LINK)
14 | Sun Aug 16, 2026 | Sun | 2 - Foundation | Hero | Carousel x3 | before-after | Same man. Different mirror. | Transformation | Week preview - 3 frames: week 2 tease / story poll (POLL) / countdown (COUNTDOWN) | Real photos + written consent
15 | Mon Aug 17, 2026 | Mon | 2 - Foundation | Hero | Static | typo | Built to disappear. | Brand | Motivation - 3 frames: built to disappear (QUOTE-SHARE) / founder note / week tease
16 | Tue Aug 18, 2026 | Tue | 2 - Foundation | Hero | Carousel x7 | how-it-works | The five base types, explained. | Education | Tips - 3 frames: mono tip / base quiz (QUIZ) / carousel pointer (LINK)
17 | Wed Aug 19, 2026 | Wed | 2 - Foundation | Hero | Reel ~25s | apply-and-go reel | On. Out the door. (Skin Frontal) | Product | Product - 3 frames: coverage line / application step / full apply (LINK)
18 | Thu Aug 20, 2026 | Thu | 2 - Foundation | Hero | Static | quote | Best money I've spent on myself in a decade. | Social Proof | Q&A - 4 frames: intro / swim question / shipping (live policy only) / question box (Q-BOX) | REQUIRES REAL QUOTE + consent
19 | Fri Aug 21, 2026 | Fri | 2 - Foundation | Hero | Reel ~30s | BTS reel | What's on the table this week. | Lifestyle | BTS - 4 frames: Friday wrap / shipped today / BTS poll (POLL) / tomorrow tease
20 | Sat Aug 22, 2026 | Sat | 2 - Foundation | Hero | Static | product | Thin Skin Pro - 0.08mm poly, lighter feel at the edge. | Product | Lifestyle - 2 frames: grooming bench (SLIDER) / up close (LINK) | Verify price
21 | Sun Aug 23, 2026 | Sun | 2 - Foundation | Hero | Carousel x5 | how-it-works | How to choose your first system in 5 minutes. | Education | Week preview - 3 frames: week 3 tease / quiz (QUIZ) / countdown (COUNTDOWN)
22 | Mon Aug 24, 2026 | Mon | 2 - Foundation | Hero | Static | typo (ink) | No one has to know. That's the point. | Brand | Motivation - 3 frames: discretion line (QUOTE-SHARE) / founder note / color week tease | 9-tile check before posting
23 | Tue Aug 25, 2026 | Tue | 2 - Foundation | Hero | Static | typo editorial | Color matching, honestly explained. | Education | Tips - 3 frames: temples tip / swatch ring / DM COLOR (LINK)
24 | Wed Aug 26, 2026 | Wed | 2 - Foundation | Hero | Static | product | Lace Fusion VF - lace comfort, easier bonding. | Product | Product - 3 frames: benefits / PU perimeter macro / specs (LINK) | Verify price
25 | Thu Aug 27, 2026 | Thu | 2 - Foundation | Hero | Reel ~30s | testimonial reel | His words, not ours. (customer voiceover) | Social Proof | Q&A - 4 frames: intro / 2 answered DMs / question box (Q-BOX) | REAL CUSTOMER + consent
26 | Fri Aug 28, 2026 | Fri | 2 - Foundation | Hero | Static | photo editorial | Rio, 6am - why I work before the city wakes. | Lifestyle | BTS - 3 frames: sunrise balcony / packed before 9 / morning poll (POLL)
27 | Sat Aug 29, 2026 | Sat | 2 - Foundation | Hero | Static | product | Hair Care Kit - what every wearer actually needs. | Product | Lifestyle - 2 frames: grooming bench (SLIDER) / kit explained (LINK) | Verify kit name/price
28 | Sun Aug 30, 2026 | Sun | 2 - Foundation | Hero | Carousel x3 | before-after | Customer No. 1 - the full arc. | Transformation | Week preview - 3 frames: month one closes / feedback poll (POLL) / countdown (COUNTDOWN) | Real photos + written consent
29 | Mon Aug 31, 2026 | Mon | 2 - Foundation | Hero | Reel ~60s | founder education reel | How a system actually fits. | Founder | Motivation - 3 frames: fit first (QUOTE-SHARE) / bust demo / reel pointer (LINK)
30 | Tue Sep 01, 2026 | Tue | 2 - Foundation | Hero | Static | typo (ink) | September 1. New month, same standard. | Brand | Tips - 3 frames: month 2 tease / 30-day recap / what to teach (Q-BOX) | 9-tile check before posting
31 | Wed Sep 02, 2026 | Wed | 3 - Resonance | Hero | Static | product | Lace Pro (French lace, $279) - Refined. Photographable. | Product | Weekly rhythm: Product spotlight (LINK) - 2-5 frames | Verify price
32 | Thu Sep 03, 2026 | Thu | 3 - Resonance | Hero | Static | quote | I stopped wearing hats. | Social Proof | Weekly rhythm: Community Q&A (Q-BOX) - 2-5 frames | REQUIRES REAL QUOTE + consent
33 | Fri Sep 04, 2026 | Fri | 3 - Resonance | Hero | Reel | BTS reel | Photoshoot day with Barry. | Lifestyle | Weekly rhythm: Behind the scenes (POLL) - 2-5 frames
34 | Sat Sep 05, 2026 | Sat | 3 - Resonance | Hero | Static | product | Mono workhorse - The everyday one. | Product | Weekly rhythm: Lifestyle (SLIDER) - 2-5 frames | Verify product name
35 | Sun Sep 06, 2026 | Sun | 3 - Resonance | Hero | Carousel x3 | before-after | Customer No. 2 - six months in. | Transformation | Weekly rhythm: Week preview (COUNTDOWN) - 2-5 frames | Real photos + consent
36 | Mon Sep 07, 2026 | Mon | 3 - Resonance | Hero | Static | typo | We don't sell hair. We sell mornings. | Brand | Weekly rhythm: Motivation (QUOTE-SHARE) - 2-5 frames | Labor Day caption
37 | Tue Sep 08, 2026 | Tue | 3 - Resonance | Hero | Carousel x5 | how-it-works | What to gift the man rebuilding his look. | Lifestyle | Weekly rhythm: Tips (LINK) - 2-5 frames
38 | Wed Sep 09, 2026 | Wed | 3 - Resonance | Hero | Reel | product routine reel | The full care routine, 30 seconds. | Product | Weekly rhythm: Product spotlight (LINK) - 2-5 frames
39 | Thu Sep 10, 2026 | Thu | 3 - Resonance | Hero | Static | quote | Took me a year to try. Wish I'd done it sooner. | Social Proof | Weekly rhythm: Community Q&A (Q-BOX) - 2-5 frames | REQUIRES REAL QUOTE + consent
40 | Fri Sep 11, 2026 | Fri | 3 - Resonance | Hero | Static | photo editorial | What we got right and wrong this season. | Lifestyle | Weekly rhythm: Behind the scenes (POLL) - 2-5 frames
41 | Sat Sep 12, 2026 | Sat | 3 - Resonance | Hero | Reel | transformation reel | 3-second reveal, slow-mo turn. | Transformation | Weekly rhythm: Lifestyle (SLIDER) - 2-5 frames | Consent; ink cover
42 | Sun Sep 13, 2026 | Sun | 3 - Resonance | Hero | Carousel x5 | how-it-works | Density 80 / 100 / 130 - what each actually looks like. | Education | Weekly rhythm: Week preview (COUNTDOWN) - 2-5 frames
43 | Mon Sep 14, 2026 | Mon | 3 - Resonance | Hero | Static | typo | Made by hand. Inspected by one. | Brand | Weekly rhythm: Motivation (QUOTE-SHARE) - 2-5 frames
44 | Tue Sep 15, 2026 | Tue | 3 - Resonance | Hero | Carousel x5 | how-it-works | Color match in 4 minutes, without leaving your bathroom. | Education | Weekly rhythm: Tips (LINK) - 2-5 frames
45 | Wed Sep 16, 2026 | Wed | 3 - Resonance | Hero | Static | product | Micro Skin ($219) - The thinnest edge we offer. | Product | Weekly rhythm: Product spotlight (LINK) - 2-5 frames | Verify price
46 | Thu Sep 17, 2026 | Thu | 3 - Resonance | Hero | Reel | Q&A reel | 5 DMs I got this week - answered. | Social Proof | Weekly rhythm: Community Q&A (Q-BOX) - 2-5 frames
47 | Fri Sep 18, 2026 | Fri | 3 - Resonance | Hero | Static | typo editorial | How long a system actually lasts (and what kills them faster). | Education | Weekly rhythm: Behind the scenes (POLL) - 2-5 frames
48 | Sat Sep 19, 2026 | Sat | 3 - Resonance | Hero | Static | product | Adhesive Remover - The unsung hero. | Product | Weekly rhythm: Lifestyle (SLIDER) - 2-5 frames | Verify name/price
49 | Sun Sep 20, 2026 | Sun | 3 - Resonance | Hero | Carousel x3 | before-after | Customer No. 3 - the first system. | Transformation | Weekly rhythm: Week preview (COUNTDOWN) - 2-5 frames | Real photos + consent
50 | Mon Sep 21, 2026 | Mon | 3 - Resonance | Hero | Reel | founder reel | Day 50. What I've learned posting every day. | Founder | Weekly rhythm: Motivation (QUOTE-SHARE) - 2-5 frames
51 | Tue Sep 22, 2026 | Tue | 3 - Resonance | Hero | Static | typo editorial | Why I don't recommend the cheapest system on the market. | Education | Weekly rhythm: Tips (LINK) - 2-5 frames
52 | Wed Sep 23, 2026 | Wed | 3 - Resonance | Hero | Static | product | Nano Skin ($269) - 0.03mm. Our lowest profile. | Product | Weekly rhythm: Product spotlight (LINK) - 2-5 frames | Verify price
53 | Thu Sep 24, 2026 | Thu | 3 - Resonance | Hero | Static | quote | Vincent answered my DM at 2am. From Brazil. | Social Proof | Weekly rhythm: Community Q&A (Q-BOX) - 2-5 frames | REQUIRES REAL QUOTE + consent
54 | Fri Sep 25, 2026 | Fri | 3 - Resonance | Hero | Reel | BTS reel | Packing week - what ships on Friday. | Lifestyle | Weekly rhythm: Behind the scenes (POLL) - 2-5 frames
55 | Sat Sep 26, 2026 | Sat | 3 - Resonance | Hero | Static | typo | Independence - the small kind. | Brand | Weekly rhythm: Lifestyle (SLIDER) - 2-5 frames
56 | Sun Sep 27, 2026 | Sun | 3 - Resonance | Hero | Static | promo | A welcome, not a sale. 10% off your first system this week. CODE FIRST10 | Sale | Weekly rhythm: Week preview (COUNTDOWN) - 2-5 frames | Cream tile; no urgency theater
57 | Mon Sep 28, 2026 | Mon | 4 - Conversion | Hero | Static | typo | Two months in. Same standard. | Brand | Weekly rhythm: Motivation (QUOTE-SHARE) - 2-5 frames
58 | Tue Sep 29, 2026 | Tue | 4 - Conversion | Hero | Carousel x5 | how-it-works | Sweat, gym, and hair systems - what actually works. | Education | Weekly rhythm: Tips (LINK) - 2-5 frames
59 | Wed Sep 30, 2026 | Wed | 4 - Conversion | Hero | Reel | product macro reel | Skin Frontal - texture, up close. | Product | Weekly rhythm: Product spotlight (LINK) - 2-5 frames
60 | Thu Oct 01, 2026 | Thu | 4 - Conversion | Hero | Static | quote | The first hairline that fooled my barber. | Social Proof | Weekly rhythm: Community Q&A (Q-BOX) - 2-5 frames | REQUIRES REAL QUOTE + consent
61 | Fri Oct 02, 2026 | Fri | 4 - Conversion | Hero | Reel | BTS reel | Studio note - Yago's first photoshoot. | Lifestyle | Weekly rhythm: Behind the scenes (POLL) - 2-5 frames
62 | Sat Oct 03, 2026 | Sat | 4 - Conversion | Hero | Static | product | Custom Hair System - The made-for-you tier. | Product | Weekly rhythm: Lifestyle (SLIDER) - 2-5 frames | Verify offering
63 | Sun Oct 04, 2026 | Sun | 4 - Conversion | Hero | Carousel x3 | before-after | Customer No. 4 - ninety days. | Transformation | Weekly rhythm: Week preview (COUNTDOWN) - 2-5 frames | Real photos + consent
64 | Mon Oct 05, 2026 | Mon | 4 - Conversion | Hero | Static | typo (ink) | The best compliment is silence. | Brand | Weekly rhythm: Motivation (QUOTE-SHARE) - 2-5 frames | 9-tile check
65 | Tue Oct 06, 2026 | Tue | 4 - Conversion | Hero | Static | typo editorial | The 5 questions to ask before buying your first system. | Education | Weekly rhythm: Tips (LINK) - 2-5 frames
66 | Wed Oct 07, 2026 | Wed | 4 - Conversion | Hero | Static | product | Micro Skin MD ($269) | Product | Weekly rhythm: Product spotlight (LINK) - 2-5 frames | Verify claim wording - no medical claims
67 | Thu Oct 08, 2026 | Thu | 4 - Conversion | Hero | Reel | testimonial reel | Customer on camera - 30s, no script. | Social Proof | Weekly rhythm: Community Q&A (Q-BOX) - 2-5 frames | Real customer + consent
68 | Fri Oct 09, 2026 | Fri | 4 - Conversion | Hero | Static | photo editorial | Rio at sunrise - why I shoot product before 7am. | Lifestyle | Weekly rhythm: Behind the scenes (POLL) - 2-5 frames
69 | Sat Oct 10, 2026 | Sat | 4 - Conversion | Hero | Reel | transformation reel | Side-by-side reveal, 8 seconds. | Transformation | Weekly rhythm: Lifestyle (SLIDER) - 2-5 frames | Consent; ink cover
70 | Sun Oct 11, 2026 | Sun | 4 - Conversion | Hero | Carousel x5 | how-it-works | Make a system last twice as long. | Education | Weekly rhythm: Week preview (COUNTDOWN) - 2-5 frames
71 | Mon Oct 12, 2026 | Mon | 4 - Conversion | Hero | Reel | founder reel | Why I personally inspect every order. | Founder | Weekly rhythm: Motivation (QUOTE-SHARE) - 2-5 frames
72 | Tue Oct 13, 2026 | Tue | 4 - Conversion | Hero | Carousel x5 | how-it-works | Maintenance - daily, weekly, monthly. | Education | Weekly rhythm: Tips (LINK) - 2-5 frames
73 | Wed Oct 14, 2026 | Wed | 4 - Conversion | Hero | Static | product | Tape & Adhesive Set - The bond, simplified. | Product | Weekly rhythm: Product spotlight (LINK) - 2-5 frames | Verify name/price
74 | Thu Oct 15, 2026 | Thu | 4 - Conversion | Hero | Static | quote | Six months. Still my system. Still my confidence. | Social Proof | Weekly rhythm: Community Q&A (Q-BOX) - 2-5 frames | REQUIRES REAL QUOTE + consent
75 | Fri Oct 16, 2026 | Fri | 4 - Conversion | Hero | Reel | BTS reel | Packing your order - the last 10 minutes. | Lifestyle | Weekly rhythm: Behind the scenes (POLL) - 2-5 frames
76 | Sat Oct 17, 2026 | Sat | 4 - Conversion | Hero | Static | product | Lace Elite ($329) - Top of the lace range. | Product | Weekly rhythm: Lifestyle (SLIDER) - 2-5 frames | Verify price
77 | Sun Oct 18, 2026 | Sun | 4 - Conversion | Hero | Carousel x3 | before-after | Customer No. 5. | Transformation | Weekly rhythm: Week preview (COUNTDOWN) - 2-5 frames | Real photos + consent
78 | Mon Oct 19, 2026 | Mon | 4 - Conversion | Hero | Static | typo | There's no version of you that needs to apologize for this. | Brand | Weekly rhythm: Motivation (QUOTE-SHARE) - 2-5 frames
79 | Tue Oct 20, 2026 | Tue | 4 - Conversion | Hero | Static | typo editorial | Hair transplants vs hair systems - the honest comparison. | Education | Weekly rhythm: Tips (LINK) - 2-5 frames | No medical claims
80 | Wed Oct 21, 2026 | Wed | 4 - Conversion | Hero | Reel | product film | Lace Pro - 12s editorial film. | Product | Weekly rhythm: Product spotlight (LINK) - 2-5 frames
81 | Thu Oct 22, 2026 | Thu | 4 - Conversion | Hero | Static | quote | Wore it on my wedding day. No one knew. | Social Proof | Weekly rhythm: Community Q&A (Q-BOX) - 2-5 frames | REQUIRES REAL QUOTE + consent
82 | Fri Oct 23, 2026 | Fri | 4 - Conversion | Hero | Static | promo | Fall note: 15% off select systems through Oct 29. CODE FALL15 | Sale | Weekly rhythm: Behind the scenes (POLL) - 2-5 frames | Cream tile; pair with Day 83 reel
83 | Sat Oct 24, 2026 | Sat | 4 - Conversion | Hero | Reel | sale support reel | Featured systems on sale - 6s x 3 cuts. | Sale | Weekly rhythm: Lifestyle (SLIDER) - 2-5 frames
84 | Sun Oct 25, 2026 | Sun | 4 - Conversion | Hero | Carousel x5 | how-it-works | The case for owning two - building a rotation. | Education | Weekly rhythm: Week preview (COUNTDOWN) - 2-5 frames
85 | Mon Oct 26, 2026 | Mon | 4 - Conversion | Hero | Reel | founder reel | Day 85. Looking back at the first seven posts. | Founder | Weekly rhythm: Motivation (QUOTE-SHARE) - 2-5 frames
86 | Tue Oct 27, 2026 | Tue | 4 - Conversion | Hero | Carousel x5 | before-after | Five transformations from this season. | Transformation | Weekly rhythm: Tips (LINK) - 2-5 frames | Real photos + consent
87 | Wed Oct 28, 2026 | Wed | 4 - Conversion | Hero | Static | product | Care & Maintenance Bundle. | Product | Weekly rhythm: Product spotlight (LINK) - 2-5 frames | Verify name/price
88 | Thu Oct 29, 2026 | Thu | 4 - Conversion | Hero | Static | quote | Closing quote slot. | Social Proof | Weekly rhythm: Community Q&A (Q-BOX) - 2-5 frames | REQUIRES REAL QUOTE + consent
89 | Fri Oct 30, 2026 | Fri | 4 - Conversion | Hero | Reel | BTS reel | What's next - 30 seconds of season two. | Brand | Weekly rhythm: Behind the scenes (POLL) - 2-5 frames
90 | Sat Oct 31, 2026 | Sat | 4 - Conversion | Hero | Static | photo typo | Ninety days. Same standard. Different chapter. | Brand | Weekly rhythm: Lifestyle (SLIDER) - 2-5 frames

## Stories Rhythm
Weekday | Concept | Frames | Sticker | Feeds highlight
Monday | Motivation - quote or founder note | 3-5 | Quote share | Start Here / About
Tuesday | Tips - one specific care tip | 3-4 | Save reminder + link | Guides
Wednesday | Product spotlight - one product, 3 benefits | 2-3 | Link to product page | Products
Thursday | Community Q&A - 3-5 anonymized DMs | 5+ | Question box | FAQ
Friday | Behind the scenes - studio, QC, packing, Rio | 4-6 | Poll | About
Saturday | Lifestyle - weekend, grooming, Rio life | 2-3 | Emoji slider | -
Sunday | Week preview - tease Monday | 3-4 | Countdown | Start Here
Highlights to build on Day 1: Start Here, Products, Reviews, Guides, Results, FAQ, Offers, About (ink + cream covers, line icons).